## Overview
FloKit.AI — Phased Build Plan
Internal Design Document — June 1, 2026
Phase Summary
Phase | Name | Duration | Tracks | Key Unlock
0 | Foundation | 3–4 weeks | 6 | Event pipeline + data models live
1 | Core Services | 5–6 weeks | 6 | MoR, paywall, web funnel, console skeleton
2 | Integration & Intelligence | 5–6 weeks | 6 | Channels connected, lifecycle running, data flowing
3 | AI Agent Layer | 5–7 weeks | 5 | Agents operating autonomously within guardrails
4 | Advanced Commerce & Growth | 4–5 weeks | 4 | Financing, ASO, churn prediction, AI surfaces
TOTAL | — | 22–28 weeks | 27 | Full platform
Critical Path
Event Pipeline (P0-D) → Subscription State Machine (P1-A) → Lifecycle State Machine (P2-C) → Segment Engine (P2-D) → Training Data Pipeline (P3-A) → Offer Scoring Agent (P3-A) → Meta-Agent Arbitration (P3-B)
Effort Legend
S | Small (~1 week)
M | Medium (~1–2 weeks)
L | Large (~2–3 weeks)
XL | Extra Large (~3–4 weeks)

## All Tasks
Task ID | Phase | Track ID | Track Name | Task Name | Description | Deliverable | Depends On | Parallel With | Effort | Status
P0-A1 | 0 | P0-A | Infrastructure | Cloud setup | Cloud provider (AWS/GCP), VPC, networking, IAM | Live dev/staging/prod | — | P0-B1,P0-C1,P0-D1 | M | Not Started
P0-A2 | 0 | P0-A | Infrastructure | CI/CD pipeline | Lint, test, build, deploy per service | Every repo auto-deploys on merge | P0-A1 | — | S | Not Started
P0-A3 | 0 | P0-A | Infrastructure | Secrets management | Vault or cloud-native, env separation | No secrets in code | P0-A1 | P0-A2 | S | Not Started
P0-A4 | 0 | P0-A | Infrastructure | Observability stack | Logging, metrics, distributed tracing | Dashboards + alerting live | P0-A1 | P0-A2 | M | Not Started
P0-A5 | 0 | P0-A | Infrastructure | Database provisioning | Postgres, Redis, ClickHouse/TimescaleDB | All datastores up, backup/restore tested | P0-A1 | — | M | Not Started
P0-B1 | 0 | P0-B | Data Models | Schema design | App, Team, User, Event, Offer, Subscription, Campaign, Paywall, CreativeAsset | ERD + reviewed schema | — | P0-A1 | L | Not Started
P0-B2 | 0 | P0-B | Data Models | Migration framework | Flyway or Alembic setup | Schema versioning workflow | P0-B1 | — | S | Not Started
P0-B3 | 0 | P0-B | Data Models | Seed data | Realistic test fixtures for all entities | Dev env bootstraps with test data | P0-B2 | — | S | Not Started
P0-B4 | 0 | P0-B | Data Models | Data access layer | Repositories/DAOs — pure CRUD | Tested data layer for all entities | P0-B2 | — | M | Not Started
P0-C1 | 0 | P0-C | Auth & Identity | Developer auth | Team login, API keys, JWT-based | Teams can sign up, log in, generate keys | P0-B4 | — | M | Not Started
P0-C2 | 0 | P0-C | Auth & Identity | RBAC model | Owner/Admin/Developer/Viewer per App | Permission checks middleware | P0-C1 | — | S | Not Started
P0-C3 | 0 | P0-C | Auth & Identity | Consumer identity | device_id, email, anon_id → unified user record | Identity graph service | P0-B4 | P0-C1 | M | Not Started
P0-C4 | 0 | P0-C | Auth & Identity | SDK key validation | Rate-limited, scoped to App | All SDK calls authenticated | P0-C1 | — | S | Not Started
P0-D1 | 0 | P0-D | Event Pipeline | Event schema | Standard envelope: event_type, user_id, app_id, timestamp, properties, session_id, region | Schema doc + validation library | P0-B1 | — | M | Not Started
P0-D2 | 0 | P0-D | Event Pipeline | Ingest API | POST /events — high-throughput, validates, writes to queue | >10k events/sec | P0-D1 | — | M | Not Started
P0-D3 | 0 | P0-D | Event Pipeline | Event queue | Kafka or SQS/SNS, topics per event category | Events durably queued | P0-D2 | — | M | Not Started
P0-D4 | 0 | P0-D | Event Pipeline | Event consumers | Fan-out to analytics, user profile, real-time state | Events in all stores within <2s | P0-D3 | — | L | Not Started
P0-D5 | 0 | P0-D | Event Pipeline | Event replay | Reprocess historical events for backfills | Replay pipeline documented and tested | P0-D4 | — | M | Not Started
P0-E1 | 0 | P0-E | SDK Skeleton | iOS SDK | Init, identity, event emission | Swift package, publishable to SPM | P0-D1 | P0-E2,P0-E3 | M | Not Started
P0-E2 | 0 | P0-E | SDK Skeleton | Android SDK | Init, identity, event emission | Kotlin library, publishable to Maven | P0-D1 | P0-E1,P0-E3 | M | Not Started
P0-E3 | 0 | P0-E | SDK Skeleton | Web JS snippet | Init, identity, event emission | CDN-hostable script snippet | P0-D1 | P0-E1,P0-E2 | S | Not Started
P0-E4 | 0 | P0-E | SDK Skeleton | SDK test harness | Simulates full user session end-to-end | Automated tests validating event emission | P0-E1,P0-E2,P0-E3 | — | M | Not Started
P0-F1 | 0 | P0-F | Service Arch | API gateway | Routing, auth middleware, rate limiting, versioning /v1/ | Single entry point for all APIs | P0-C2 | — | M | Not Started
P0-F2 | 0 | P0-F | Service Arch | Service registry | Inter-service comms (REST or gRPC, OpenAPI) | Contract-first API specs | P0-F1 | — | M | Not Started
P0-F3 | 0 | P0-F | Service Arch | Background jobs | Celery, BullMQ, or Temporal | Workers run scheduled + triggered jobs | P0-A1 | P0-F1 | M | Not Started
P0-F4 | 0 | P0-F | Service Arch | Feature flags | Internal feature flag system | Features toggled per App without deploy | P0-F1 | — | S | Not Started
P1-A1 | 1 | P1-A | Subscription & MoR | MoR interface | createSubscription, cancelSubscription, getStatus, issueRefund | Provider-agnostic interface | P0-B4 | — | M | Not Started
P1-A2 | 1 | P1-A | Subscription & MoR | Stripe integration | Implement MoR interface for Stripe Billing | Stripe webhooks handled | P1-A1 | P1-A3,P1-A4 | M | Not Started
P1-A3 | 1 | P1-A | Subscription & MoR | RevenueCat integration | Implement MoR interface for RevenueCat | RevenueCat synced | P1-A1 | P1-A2,P1-A4 | M | Not Started
P1-A4 | 1 | P1-A | Subscription & MoR | Paddle integration | Implement MoR interface for Paddle | Paddle synced | P1-A1 | P1-A2,P1-A3 | M | Not Started
P1-A5 | 1 | P1-A | Subscription & MoR | Subscription state machine | trialing→active→past_due→canceled→winback_eligible | State transitions fire events | P1-A2 | — | L | Not Started
P1-A6 | 1 | P1-A | Subscription & MoR | Dunning logic | Payment retry D1, D3, D7 post-failure | Automated retry with configurable schedule | P1-A5 | — | M | Not Started
P1-A7 | 1 | P1-A | Subscription & MoR | Entitlement service | hasAccess(user_id, feature) | Single source of truth for paid access | P1-A5 | — | M | Not Started
P1-A8 | 1 | P1-A | Subscription & MoR | Webhook normalization | All MoR webhooks → standard subscription.* events | Unified event format | P1-A2,P1-A3,P1-A4 | — | M | Not Started
P1-B1 | 1 | P1-B | Offer Catalog | Offer data model | type, price_point, currency, trial_days, copy, creative_ref, conditions | Schema migrated and tested | P0-B2 | — | M | Not Started
P1-B2 | 1 | P1-B | Offer Catalog | Offer CRUD API | Create, update, archive, list per App | REST API with validation | P1-B1 | — | M | Not Started
P1-B3 | 1 | P1-B | Offer Catalog | Offer templates | 3–5 pre-built templates per vertical | Templates for fitness, education, productivity | P1-B1 | P1-B2 | M | Not Started
P1-B4 | 1 | P1-B | Offer Catalog | Conditions engine | isEligible(offer, user_context) → bool | Evaluates segment_match, timing_rule, region_rule | P1-B2 | — | M | Not Started
P1-B5 | 1 | P1-B | Offer Catalog | Offer versioning | Immutable history of offer changes | Offers versioned; experiments reference version IDs | P1-B2 | — | S | Not Started
P1-C1 | 1 | P1-C | Web-to-App | Landing page engine | Parameterized pages per App | Unique landing page URLs per campaign | P0-F1 | — | L | Not Started
P1-C2 | 1 | P1-C | Web-to-App | Session tracking | Anonymous session ID, UTM capture, scroll/click events | Emits web_visit, cta_click events | P1-C1,P0-D2 | — | M | Not Started
P1-C3 | 1 | P1-C | Web-to-App | Web checkout | Email → Stripe payment → issue subscription | Users pay on web before installing | P1-A2,P1-C2 | P1-C4 | L | Not Started
P1-C4 | 1 | P1-C | Web-to-App | Deferred deeplink | Generate deeplink with session_id; resolves on first-open | App receives web session context | P1-C2 | P1-C3 | M | Not Started
P1-C5 | 1 | P1-C | Web-to-App | Attribution join | web_session_id → install → first_open → subscription | Attribution record per user | P1-C2,P1-C4 | — | M | Not Started
P1-C6 | 1 | P1-C | Web-to-App | App Store redirect | UTM-tagged + SKAdNetwork (iOS) + referrer API (Android) | Installs measurable from this path | P0-E1,P0-E2 | P1-C3 | M | Not Started
P1-C7 | 1 | P1-C | Web-to-App | Funnel monitoring | Calculate conversion rate at each step; alert on breach | Alerting rules + funnel metrics | P1-C5 | — | M | Not Started
P1-D1 | 1 | P1-D | Paywall & Experiments | Experiment service | Create experiment, assign arms deterministically by user_id | getArm(experiment_id, user_id) → arm | P0-C3 | — | L | Not Started
P1-D2 | 1 | P1-D | Paywall & Experiments | Significance calculator | Automated winner detection with configurable confidence | Flags when winner is found | P1-D1 | — | M | Not Started
P1-D3 | 1 | P1-D | Paywall & Experiments | Paywall config API | getPaywall(user_id, app_id) → {layout, offers, experiment_arm} | Correct paywall per user | P1-D1,P1-B4 | — | M | Not Started
P1-D4 | 1 | P1-D | Paywall & Experiments | iOS paywall module | Renders paywall from config, fires paywall_view, offer_tap events | Native paywall UI in iOS SDK | P1-D3,P0-E1 | P1-D5 | L | Not Started
P1-D5 | 1 | P1-D | Paywall & Experiments | Android paywall module | Same as D4 for Android | Native paywall UI in Android SDK | P1-D3,P0-E2 | P1-D4 | L | Not Started
P1-D6 | 1 | P1-D | Paywall & Experiments | Holdout groups | Reserve % of traffic as unexposed control | Valid baseline for all experiments | P1-D1 | — | S | Not Started
P1-E1 | 1 | P1-E | Console Frontend | Design system | Shared UI components, layout, theme | Reusable design system | — | — | L | Not Started
P1-E2 | 1 | P1-E | Console Frontend | Auth screens | Login, team setup, invite, API key management | Developers can log in and set up App | P0-C1,P1-E1 | — | M | Not Started
P1-E3 | 1 | P1-E | Console Frontend | App setup wizard | Add App, connect MoR, SDK install instructions | New dev onboarded in <15 min | P1-A1,P1-E1 | P1-E2 | M | Not Started
P1-E4 | 1 | P1-E | Console Frontend | Offer management | List, create, edit, archive offers; view performance | Full offer CRUD in UI | P1-B2,P1-E1 | — | M | Not Started
P1-E5 | 1 | P1-E | Console Frontend | Experiment dashboard | Active experiments, arm traffic, CVR, winner callout | Manage A/B tests without code | P1-D1,P1-E1 | — | M | Not Started
P1-E6 | 1 | P1-E | Console Frontend | Funnel overview | install→trial→paid→retained waterfall, filterable | Core KPI view | P1-C5,P1-E1 | — | L | Not Started
P1-F1 | 1 | P1-F | Compliance | Audit log service | Every write action appended to immutable log | auditLog.write(action, actor, entity, before, after) | P0-B4 | — | M | Not Started
P1-F2 | 1 | P1-F | Compliance | Consent propagation | GDPR opt-out on user record → no events emitted | GDPR opt-out respected everywhere | P0-C3,P0-D4 | — | M | Not Started
P1-F3 | 1 | P1-F | Compliance | Data residency | Events tagged with region, routed to regional storage | Events stored in compliant region | P0-D4 | — | M | Not Started
P1-F4 | 1 | P1-F | Compliance | COPPA controls | Age gate flag; under-13 excluded from personalization | Personalization checks flag before acting | P0-C3 | — | S | Not Started
P1-F5 | 1 | P1-F | Compliance | Data retention | Automated purge jobs per region | Scheduled jobs enforce retention windows | P1-F3 | — | M | Not Started
P2-A1 | 2 | P2-A | Channel Integrations | Channel interface | createCampaign, updateBudget, pauseCreative, pullMetrics | Provider-agnostic interface | P0-F2 | — | M | Not Started
P2-A2 | 2 | P2-A | Channel Integrations | Meta integration | Facebook/Instagram via Meta Marketing API | Meta campaigns manageable from FloKit | P2-A1 | P2-A3 | L | Not Started
P2-A3 | 2 | P2-A | Channel Integrations | AppLovin integration | AppLovin Campaigns API | AppLovin campaigns manageable | P2-A1 | P2-A2 | L | Not Started
P2-A4 | 2 | P2-A | Channel Integrations | Metrics normalization | Normalize to {impressions, clicks, installs, cost, revenue} | Unified campaign metrics table | P2-A2,P2-A3 | — | M | Not Started
P2-A5 | 2 | P2-A | Channel Integrations | Campaign builder | Audience spec + creative set + budget → call channel API | createCampaign(spec) → campaign_id | P2-A4,P2-B5 | — | L | Not Started
P2-A6 | 2 | P2-A | Channel Integrations | Performance pull job | Daily metrics from all channels → analytics DB | Campaign performance in console | P2-A4 | — | M | Not Started
P2-B1 | 2 | P2-B | Creative Generation | App catalog ingestion | Parse App Store URL: screenshots, description, metadata | App.catalog populated | P0-F3 | — | M | Not Started
P2-B2 | 2 | P2-B | Creative Generation | Copy generation | LLM → headline variants, CTAs, body copy per audience | N copy variants per brief | P2-B1 | P2-B3 | M | Not Started
P2-B3 | 2 | P2-B | Creative Generation | Image generation | Channel-appropriate dimensions (1:1, 9:16, 1.91:1) | Static creative assets | P2-B1 | P2-B2,P2-B4 | L | Not Started
P2-B4 | 2 | P2-B | Creative Generation | Video generation | 15s/30s video variants | Video assets | P2-B1 | P2-B2,P2-B3 | L | Not Started
P2-B5 | 2 | P2-B | Creative Generation | Creative composition | Overlay copy on visuals, brand kit, export per channel spec | Final assets ready for upload | P2-B2,P2-B3 | — | M | Not Started
P2-B6 | 2 | P2-B | Creative Generation | Creative library | Store all assets with metadata | Searchable asset library | P2-B5 | — | M | Not Started
P2-B7 | 2 | P2-B | Creative Generation | Performance tagging | Link creative_id to campaign metrics | Each asset has CTR/CVR track record | P2-B6,P2-A6 | — | M | Not Started
P2-C1 | 2 | P2-C | Lifecycle Engine | Lifecycle state machine | anonymous→trial→subscribed→at_risk→churned→winback_eligible | State machine consuming subscription events | P1-A5 | — | L | Not Started
P2-C2 | 2 | P2-C | Lifecycle Engine | Trigger engine | {state=trial, days=3, sessions<2} → fire activation_email | Triggers on every user state change | P2-C1 | — | L | Not Started
P2-C3 | 2 | P2-C | Lifecycle Engine | Email templates | Activation, nudge, renewal, dunning, win-back; LLM personalizes | Template library with variable substitution | — | — | M | Not Started
P2-C4 | 2 | P2-C | Lifecycle Engine | Email sending | Wraps SendGrid/Postmark/SES; unsubscribes, bounces | Reliable delivery with deliverability tracking | P2-C3 | — | M | Not Started
P2-C5 | 2 | P2-C | Lifecycle Engine | Send-time optimization | Per-user model of historical open rates by hour | Emails sent at optimal times | P2-C4 | — | M | Not Started
P2-C6 | 2 | P2-C | Lifecycle Engine | In-app messaging | Push notification or in-app banner via SDK | sendInAppMessage(user_id, template_id) | P0-E1,P0-E2,P2-C2 | P2-C4 | M | Not Started
P2-C7 | 2 | P2-C | Lifecycle Engine | Frequency cap | Max N contacts per 7-day rolling window across all channels | No user over-messaged | P2-C2,P2-C6 | — | M | Not Started
P2-D1 | 2 | P2-D | Segment Engine | Segment definitions | Rules-based: {country=US AND sessions>3 AND attribution=facebook} | Segment CRUD API | P0-B4 | — | M | Not Started
P2-D2 | 2 | P2-D | Segment Engine | Segment computation | Batch daily + real-time on event receipt | Every user has computed segments | P2-D1,P0-D4 | — | L | Not Started
P2-D3 | 2 | P2-D | Segment Engine | Membership API | getSegments(user_id) and getUsersInSegment(segment_id) | Fast lookup for downstream consumers | P2-D2 | — | M | Not Started
P2-D4 | 2 | P2-D | Segment Engine | Segment analytics | Size, growth, conversion rate per segment | Developers see segment behavior | P2-D3 | — | M | Not Started
P2-E1 | 2 | P2-E | Console Intelligence | Campaign management | Create/edit campaigns, assign creatives, set budget | Acquisition management in console | P2-A5,P2-B6 | — | L | Not Started
P2-E2 | 2 | P2-E | Console Intelligence | Creative library UI | Browse, preview, tag, assign assets | Visual asset management | P2-B6 | P2-E1 | M | Not Started
P2-E3 | 2 | P2-E | Console Intelligence | Lifecycle flow builder | Visual editor for trigger → action rules | Non-technical operators configure lifecycle | P2-C2 | — | L | Not Started
P2-E4 | 2 | P2-E | Console Intelligence | Segment manager | Create, name, preview segments, see membership | Segment management UI | P2-D3 | — | M | Not Started
P2-E5 | 2 | P2-E | Console Intelligence | Subscription analytics | MRR, ARR, churn rate, LTV, cohort retention | Core revenue metrics | P1-A5 | — | L | Not Started
P2-F1 | 2 | P2-F | Offer Builder | Pricing heuristics | Baseline trial/annual/monthly pricing per vertical | Pricing knowledge base | — | — | M | Not Started
P2-F2 | 2 | P2-F | Offer Builder | Competitor pricing | Parse competitor pricing from App Store category | Enriched pricing context | P2-F1 | — | M | Not Started
P2-F3 | 2 | P2-F | Offer Builder | Offer generation | LLM + heuristics → 3–5 offer candidates (type, price, trial_days, copy) | Auto-generated offer set for A/B test | P2-F2,P1-B1 | — | L | Not Started
P2-F4 | 2 | P2-F | Offer Builder | Offer generation UI | Wizard: category → review → approve → push to catalog | Offer set in minutes | P2-F3 | — | M | Not Started
P3-A1 | 3 | P3-A | Offer Scoring Agent | Feature vector | [segment, channel, time_in_app, session_count, offer_history, recency] | Feature spec document | P2-D3 | — | M | Not Started
P3-A2 | 3 | P3-A | Offer Scoring Agent | Training data pipeline | Pull historical (user_context, offer_shown, outcome) tuples | Labeled dataset for initial training | P3-A1,P0-D5 | — | L | Not Started
P3-A3 | 3 | P3-A | Offer Scoring Agent | Contextual bandit | Train model; deploy score(user_context) → [{offer_id, score}] | Scoring endpoint deployed | P3-A2 | — | XL | Not Started
P3-A4 | 3 | P3-A | Offer Scoring Agent | Dispatch service | Call scorer, select offer, respect guardrails, dispatch to surface | dispatch(user_id, surface) → offer | P3-A3,P1-B4 | — | L | Not Started
P3-A5 | 3 | P3-A | Offer Scoring Agent | Feedback loop | Conversion/dismiss events fed back to retrain model daily | Model improves over time | P3-A4 | — | M | Not Started
P3-A6 | 3 | P3-A | Offer Scoring Agent | Guardrail enforcement | Min/max price, region restrictions, experiment arm locks | No invalid offer ever shown | P3-A4,P1-D6 | — | M | Not Started
P3-B1 | 3 | P3-B | Meta-Agent | Agent registry | Catalog of all active agents per App, action domains, status | Central registry of running agents | P3-A4 | — | M | Not Started
P3-B2 | 3 | P3-B | Meta-Agent | Action arbitration | Priority rules when multiple agents want to act on same user | No conflicting actions reach same user | P3-B1 | — | L | Not Started
P3-B3 | 3 | P3-B | Meta-Agent | Budget allocation | Monitor UA spend vs projected LTV → recommend rebalancing | Weekly budget recommendation | P2-A6,P3-B1 | P3-B2 | L | Not Started
P3-B4 | 3 | P3-B | Meta-Agent | Anomaly detection | Monitor key metrics; alert on threshold breach within <1h | Alert within <1h of regression | P0-D4 | P3-B3 | L | Not Started
P3-B5 | 3 | P3-B | Meta-Agent | Agent action log | Every decision recorded with rationale, inputs, outcome | Full audit trail for autonomous actions | P1-F1,P3-B1 | — | M | Not Started
P3-C1 | 3 | P3-C | AI Commerce | Surface registry | All surfaces and rendering constraints | Surface specs document | P1-B2 | — | M | Not Started
P3-C2 | 3 | P3-C | AI Commerce | One-tap checkout | Resolve payment, charge, provision entitlement | checkout(user_id, offer_id) → {status, entitlement} | P1-A7,P3-C1 | — | L | Not Started
P3-C3 | 3 | P3-C | AI Commerce | Chatbot webhook | Accepts {user_context} → returns {offer_payload} | Chatbot can surface offers | P3-C2 | P3-C4 | M | Not Started
P3-C4 | 3 | P3-C | AI Commerce | MCP tool | FloKit exposes get_offer(user_context) as MCP tool | MCP tool spec + server deployed | P3-C3 | — | L | Not Started
P3-C5 | 3 | P3-C | AI Commerce | Email offer card | Tokenized one-click checkout link in email HTML | Offer in email → one-tap checkout | P3-C2,P2-C4 | — | M | Not Started
P3-C6 | 3 | P3-C | AI Commerce | Surface-aware selection | Agent adapts offer content to surface constraints | Each surface gets appropriate offer format | P3-A4,P3-C1 | — | M | Not Started
P3-D1 | 3 | P3-D | Creative Agent | Performance eval job | Daily CTR, CVR, cost-per-install vs benchmark | Underperformer flag on each creative | P2-A6,P2-B7 | — | M | Not Started
P3-D2 | 3 | P3-D | Creative Agent | Creative retirement | Auto-pause creatives below threshold | Underperformers stop spending | P3-D1 | — | S | Not Started
P3-D3 | 3 | P3-D | Creative Agent | Replacement generation | Retired creative triggers new variant generation | New variants auto-queued | P3-D2,P2-B5 | — | M | Not Started
P3-D4 | 3 | P3-D | Creative Agent | Creative learning | Extract signals from top performers → seed next generation | Generation prompts informed by data | P3-D3 | — | L | Not Started
P3-E1 | 3 | P3-E | Agent Console | Activity feed | Real-time stream of agent decisions with context and outcome | Operators see agents live | P3-B5 | — | L | Not Started
P3-E2 | 3 | P3-E | Agent Console | Guardrail editor | Set min/max price, max discount, region exclusions, frequency caps | Non-engineer operators constrain agents | P3-A6 | — | M | Not Started
P3-E3 | 3 | P3-E | Agent Console | Override controls | Force offer to 100% traffic, pause agent category | One-click human override | P3-B2 | — | M | Not Started
P3-E4 | 3 | P3-E | Agent Console | Recommendation surface | Agent surfaces suggestions → operator approves | Human-in-the-loop for high-impact decisions | P3-B4 | — | M | Not Started
P4-A1 | 4 | P4-A | UA Financing | LTV prediction model | Predict D30/D90 LTV from D3/D7 cohort signals | predictLTV(cohort_features) → {ltv, confidence} | P2-D2,P0-D5 | — | XL | Not Started
P4-A2 | 4 | P4-A | UA Financing | Financing flow | Developer requests UA budget; system assesses LTV; approves/declines | Approval decision with financing terms | P4-A1 | — | L | Not Started
P4-A3 | 4 | P4-A | UA Financing | Repayment tracking | As cohort revenue recognized, calculate FloKit's share | Revenue attribution and repayment ledger | P1-A7,P4-A2 | — | L | Not Started
P4-A4 | 4 | P4-A | UA Financing | Risk controls | Per-App exposure limits; performance gates | Automated risk management | P4-A3 | — | M | Not Started
P4-B1 | 4 | P4-B | ASO & AI Discovery | ASO analysis | Parse App Store page, keyword rankings vs category top 10 | ASO health score + gap analysis | P2-B1 | — | M | Not Started
P4-B2 | 4 | P4-B | ASO & AI Discovery | ASO recommendations | Suggests keyword, screenshot, and description changes | Prioritized ASO action list | P4-B1 | — | M | Not Started
P4-B3 | 4 | P4-B | ASO & AI Discovery | AI surface discovery | Monitor LLM/AI surfaces for category keywords | Alert when App surfaced in AI results | P0-F3 | P4-B1 | M | Not Started
P4-B4 | 4 | P4-B | ASO & AI Discovery | AI surface optimization | Generate descriptions optimized for AI retrieval | App appears in AI surface results | P4-B3 | — | M | Not Started
P4-C1 | 4 | P4-C | Advanced Analytics | Cohort analysis | Group users by install week × channel × segment | Cohort table in analytics DB | P2-D2,P0-D4 | — | L | Not Started
P4-C2 | 4 | P4-C | Advanced Analytics | LTV projections | D7→D30→D90→D365 LTV curves with confidence bands | Developers see predicted revenue trajectory | P4-C1 | — | L | Not Started
P4-C3 | 4 | P4-C | Advanced Analytics | Payback calculator | CAC by channel + LTV curve → days to payback | Payback period per channel | P2-A6,P4-C2 | — | M | Not Started
P4-C4 | 4 | P4-C | Advanced Analytics | Win-back analytics | Incremental revenue vs organic return rate | True incrementality measurement | P2-C2,P4-C1 | — | M | Not Started
P4-D1 | 4 | P4-D | Churn Recovery | Churn prediction | Predict churn probability in next 14 days | predictChurn(user_id) → {probability, top_signals} | P2-D2,P3-A2 | — | XL | Not Started
P4-D2 | 4 | P4-D | Churn Recovery | Proactive retention | Agent selects intervention for high-risk users before churning | At-risk users receive targeted action | P4-D1,P3-A4 | — | L | Not Started
P4-D3 | 4 | P4-D | Churn Recovery | Win-back campaigns | Escalating discount sequence over 60 days post-churn | Win-back sequence with incrementally better offers | P2-C2,P1-B2 | — | L | Not Started
P4-D4 | 4 | P4-D | Churn Recovery | Pause subscription | 30/60-day pause alternative to cancel | Pause option reduces hard churns | P1-A5 | — | M | Not Started

## Phase 0 — Foundation
Task ID | Track | Task Name | Deliverable | Effort | Depends On | Wk1 | Wk2 | Wk3 | Wk4
P0-A1 | P0-A | Cloud setup | Live dev/staging/prod | M | — | ● | ●
P0-A2 | P0-A | CI/CD pipeline | Every repo auto-deploys on merge | S | P0-A1 |  | ●
P0-A3 | P0-A | Secrets management | No secrets in code | S | P0-A1 |  |  | ●
P0-A4 | P0-A | Observability stack | Dashboards + alerting live | M | P0-A1 |  |  | ● | ●
P0-A5 | P0-A | Database provisioning | All datastores up, backup/restore tested | M | P0-A1 |  |  | ● | ●
P0-B1 | P0-B | Schema design | ERD + reviewed schema | L | — | ● | ● | ●
P0-B2 | P0-B | Migration framework | Schema versioning workflow | S | P0-B1 |  | ●
P0-B3 | P0-B | Seed data | Dev env bootstraps with test data | S | P0-B2 |  |  | ●
P0-B4 | P0-B | Data access layer | Tested data layer for all entities | M | P0-B2 |  |  | ● | ●
P0-C1 | P0-C | Developer auth | Teams can sign up, log in, generate keys | M | P0-B4 | ● | ●
P0-C2 | P0-C | RBAC model | Permission checks middleware | S | P0-C1 |  | ●
P0-C3 | P0-C | Consumer identity | Identity graph service | M | P0-B4 |  |  | ● | ●
P0-C4 | P0-C | SDK key validation | All SDK calls authenticated | S | P0-C1 |  |  |  | ●
P0-D1 | P0-D | Event schema | Schema doc + validation library | M | P0-B1 | ● | ●
P0-D2 | P0-D | Ingest API | >10k events/sec | M | P0-D1 |  | ● | ●
P0-D3 | P0-D | Event queue | Events durably queued | M | P0-D2 |  |  | ● | ●
P0-D4 | P0-D | Event consumers | Events in all stores within <2s | L | P0-D3 |  | ● | ● | ●
P0-D5 | P0-D | Event replay | Replay pipeline documented and tested | M | P0-D4 |  |  | ● | ●
P0-E1 | P0-E | iOS SDK | Swift package, publishable to SPM | M | P0-D1 | ● | ●
P0-E2 | P0-E | Android SDK | Kotlin library, publishable to Maven | M | P0-D1 |  | ● | ●
P0-E3 | P0-E | Web JS snippet | CDN-hostable script snippet | S | P0-D1 |  |  | ●
P0-E4 | P0-E | SDK test harness | Automated tests validating event emission | M | P0-E1,P0-E2,P0-E3 |  |  | ● | ●
P0-F1 | P0-F | API gateway | Single entry point for all APIs | M | P0-C2 | ● | ●
P0-F2 | P0-F | Service registry | Contract-first API specs | M | P0-F1 |  | ● | ●
P0-F3 | P0-F | Background jobs | Workers run scheduled + triggered jobs | M | P0-A1 |  |  | ● | ●
P0-F4 | P0-F | Feature flags | Features toggled per App without deploy | S | P0-F1 |  |  |  | ●

## Phase 1 — Core Services
Task ID | Track | Task Name | Deliverable | Effort | Depends On | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6
P1-A1 | P1-A | MoR interface | Provider-agnostic interface | M | P0-B4 | ● | ●
P1-A2 | P1-A | Stripe integration | Stripe webhooks handled | M | P1-A1 |  | ● | ●
P1-A3 | P1-A | RevenueCat integration | RevenueCat synced | M | P1-A1 |  |  | ● | ●
P1-A4 | P1-A | Paddle integration | Paddle synced | M | P1-A1 |  |  |  | ● | ●
P1-A5 | P1-A | Subscription state machine | State transitions fire events | L | P1-A2 |  |  |  | ● | ● | ●
P1-A6 | P1-A | Dunning logic | Automated retry with configurable schedule | M | P1-A5 |  |  |  |  | ● | ●
P1-A7 | P1-A | Entitlement service | Single source of truth for paid access | M | P1-A5 |  |  |  |  | ● | ●
P1-A8 | P1-A | Webhook normalization | Unified event format | M | P1-A2,P1-A3,P1-A4 |  |  |  |  | ● | ●
P1-B1 | P1-B | Offer data model | Schema migrated and tested | M | P0-B2 | ● | ●
P1-B2 | P1-B | Offer CRUD API | REST API with validation | M | P1-B1 |  | ● | ●
P1-B3 | P1-B | Offer templates | Templates for fitness, education, productivity | M | P1-B1 |  |  | ● | ●
P1-B4 | P1-B | Conditions engine | Evaluates segment_match, timing_rule, region_rule | M | P1-B2 |  |  |  | ● | ●
P1-B5 | P1-B | Offer versioning | Offers versioned; experiments reference version IDs | S | P1-B2 |  |  |  |  | ●
P1-C1 | P1-C | Landing page engine | Unique landing page URLs per campaign | L | P0-F1 | ● | ● | ●
P1-C2 | P1-C | Session tracking | Emits web_visit, cta_click events | M | P1-C1,P0-D2 |  | ● | ●
P1-C3 | P1-C | Web checkout | Users pay on web before installing | L | P1-A2,P1-C2 |  |  | ● | ● | ●
P1-C4 | P1-C | Deferred deeplink | App receives web session context | M | P1-C2 |  |  |  | ● | ●
P1-C5 | P1-C | Attribution join | Attribution record per user | M | P1-C2,P1-C4 |  |  |  |  | ● | ●
P1-C6 | P1-C | App Store redirect | Installs measurable from this path | M | P0-E1,P0-E2 |  |  |  |  | ● | ●
P1-C7 | P1-C | Funnel monitoring | Alerting rules + funnel metrics | M | P1-C5 |  |  |  |  | ● | ●
P1-D1 | P1-D | Experiment service | getArm(experiment_id, user_id) → arm | L | P0-C3 | ● | ● | ●
P1-D2 | P1-D | Significance calculator | Flags when winner is found | M | P1-D1 |  | ● | ●
P1-D3 | P1-D | Paywall config API | Correct paywall per user | M | P1-D1,P1-B4 |  |  | ● | ●
P1-D4 | P1-D | iOS paywall module | Native paywall UI in iOS SDK | L | P1-D3,P0-E1 |  |  |  | ● | ● | ●
P1-D5 | P1-D | Android paywall module | Native paywall UI in Android SDK | L | P1-D3,P0-E2 |  |  |  | ● | ● | ●
P1-D6 | P1-D | Holdout groups | Valid baseline for all experiments | S | P1-D1 | [5 empty] | ●
P1-E1 | P1-E | Design system | Reusable design system | L | — | ● | ● | ●
P1-E2 | P1-E | Auth screens | Developers can log in and set up App | M | P0-C1,P1-E1 |  | ● | ●
P1-E3 | P1-E | App setup wizard | New dev onboarded in <15 min | M | P1-A1,P1-E1 |  |  | ● | ●
P1-E4 | P1-E | Offer management | Full offer CRUD in UI | M | P1-B2,P1-E1 |  |  |  | ● | ●
P1-E5 | P1-E | Experiment dashboard | Manage A/B tests without code | M | P1-D1,P1-E1 |  |  |  |  | ● | ●
P1-E6 | P1-E | Funnel overview | Core KPI view | L | P1-C5,P1-E1 |  |  |  | ● | ● | ●
P1-F1 | P1-F | Audit log service | auditLog.write(action, actor, entity, before, after) | M | P0-B4 | ● | ●
P1-F2 | P1-F | Consent propagation | GDPR opt-out respected everywhere | M | P0-C3,P0-D4 |  | ● | ●
P1-F3 | P1-F | Data residency | Events stored in compliant region | M | P0-D4 |  |  | ● | ●
P1-F4 | P1-F | COPPA controls | Personalization checks flag before acting | S | P0-C3 |  |  |  | ●
P1-F5 | P1-F | Data retention | Scheduled jobs enforce retention windows | M | P1-F3 |  |  |  |  | ● | ●

## Phase 2 — Integration
Task ID | Track | Task Name | Deliverable | Effort | Depends On | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6
P2-A1 | P2-A | Channel interface | Provider-agnostic interface | M | P0-F2 | ● | ●
P2-A2 | P2-A | Meta integration | Meta campaigns manageable from FloKit | L | P2-A1 |  | ● | ● | ●
P2-A3 | P2-A | AppLovin integration | AppLovin campaigns manageable | L | P2-A1 |  |  | ● | ● | ●
P2-A4 | P2-A | Metrics normalization | Unified campaign metrics table | M | P2-A2,P2-A3 |  |  |  | ● | ●
P2-A5 | P2-A | Campaign builder | createCampaign(spec) → campaign_id | L | P2-A4,P2-B5 |  |  |  | ● | ● | ●
P2-A6 | P2-A | Performance pull job | Campaign performance in console | M | P2-A4 |  |  |  |  | ● | ●
P2-B1 | P2-B | App catalog ingestion | App.catalog populated | M | P0-F3 | ● | ●
P2-B2 | P2-B | Copy generation | N copy variants per brief | M | P2-B1 |  | ● | ●
P2-B3 | P2-B | Image generation | Static creative assets | L | P2-B1 |  |  | ● | ● | ●
P2-B4 | P2-B | Video generation | Video assets | L | P2-B1 |  |  |  | ● | ● | ●
P2-B5 | P2-B | Creative composition | Final assets ready for upload | M | P2-B2,P2-B3 |  |  |  |  | ● | ●
P2-B6 | P2-B | Creative library | Searchable asset library | M | P2-B5 |  |  |  |  | ● | ●
P2-B7 | P2-B | Performance tagging | Each asset has CTR/CVR track record | M | P2-B6,P2-A6 |  |  |  |  | ● | ●
P2-C1 | P2-C | Lifecycle state machine | State machine consuming subscription events | L | P1-A5 | ● | ● | ●
P2-C2 | P2-C | Trigger engine | Triggers on every user state change | L | P2-C1 |  | ● | ● | ●
P2-C3 | P2-C | Email templates | Template library with variable substitution | M | — |  |  | ● | ●
P2-C4 | P2-C | Email sending | Reliable delivery with deliverability tracking | M | P2-C3 |  |  |  | ● | ●
P2-C5 | P2-C | Send-time optimization | Emails sent at optimal times | M | P2-C4 |  |  |  |  | ● | ●
P2-C6 | P2-C | In-app messaging | sendInAppMessage(user_id, template_id) | M | P0-E1,P0-E2,P2-C2 |  |  |  |  | ● | ●
P2-C7 | P2-C | Frequency cap | No user over-messaged | M | P2-C2,P2-C6 |  |  |  |  | ● | ●
P2-D1 | P2-D | Segment definitions | Segment CRUD API | M | P0-B4 | ● | ●
P2-D2 | P2-D | Segment computation | Every user has computed segments | L | P2-D1,P0-D4 |  | ● | ● | ●
P2-D3 | P2-D | Membership API | Fast lookup for downstream consumers | M | P2-D2 |  |  | ● | ●
P2-D4 | P2-D | Segment analytics | Developers see segment behavior | M | P2-D3 |  |  |  | ● | ●
P2-E1 | P2-E | Campaign management | Acquisition management in console | L | P2-A5,P2-B6 | ● | ● | ●
P2-E2 | P2-E | Creative library UI | Visual asset management | M | P2-B6 |  | ● | ●
P2-E3 | P2-E | Lifecycle flow builder | Non-technical operators configure lifecycle | L | P2-C2 |  |  | ● | ● | ●
P2-E4 | P2-E | Segment manager | Segment management UI | M | P2-D3 |  |  |  | ● | ●
P2-E5 | P2-E | Subscription analytics | Core revenue metrics | L | P1-A5 |  |  |  | ● | ● | ●
P2-F1 | P2-F | Pricing heuristics | Pricing knowledge base | M | — | ● | ●
P2-F2 | P2-F | Competitor pricing | Enriched pricing context | M | P2-F1 |  | ● | ●
P2-F3 | P2-F | Offer generation | Auto-generated offer set for A/B test | L | P2-F2,P1-B1 |  |  | ● | ● | ●
P2-F4 | P2-F | Offer generation UI | Offer set in minutes | M | P2-F3 |  |  |  | ● | ●

## Phase 3 — AI Agents
Task ID | Track | Task Name | Deliverable | Effort | Depends On | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7
P3-A1 | P3-A | Feature vector | Feature spec document | M | P2-D3 | ● | ●
P3-A2 | P3-A | Training data pipeline | Labeled dataset for initial training | L | P3-A1,P0-D5 |  | ● | ● | ●
P3-A3 | P3-A | Contextual bandit | Scoring endpoint deployed | XL | P3-A2 |  |  | ● | ● | ● | ●
P3-A4 | P3-A | Dispatch service | dispatch(user_id, surface) → offer | L | P3-A3,P1-B4 |  |  |  | ● | ● | ●
P3-A5 | P3-A | Feedback loop | Model improves over time | M | P3-A4 |  |  |  |  | ● | ●
P3-A6 | P3-A | Guardrail enforcement | No invalid offer ever shown | M | P3-A4,P1-D6 | [5 empty] | ● | ●
P3-B1 | P3-B | Agent registry | Central registry of running agents | M | P3-A4 | ● | ●
P3-B2 | P3-B | Action arbitration | No conflicting actions reach same user | L | P3-B1 |  | ● | ● | ●
P3-B3 | P3-B | Budget allocation | Weekly budget recommendation | L | P2-A6,P3-B1 |  |  | ● | ● | ●
P3-B4 | P3-B | Anomaly detection | Alert within <1h of regression | L | P0-D4 |  |  |  | ● | ● | ●
P3-B5 | P3-B | Agent action log | Full audit trail for autonomous actions | M | P1-F1,P3-B1 |  |  |  |  | ● | ●
P3-C1 | P3-C | Surface registry | Surface specs document | M | P1-B2 | ● | ●
P3-C2 | P3-C | One-tap checkout | checkout(user_id, offer_id) → {status, entitlement} | L | P1-A7,P3-C1 |  | ● | ● | ●
P3-C3 | P3-C | Chatbot webhook | Chatbot can surface offers | M | P3-C2 |  |  | ● | ●
P3-C4 | P3-C | MCP tool | MCP tool spec + server deployed | L | P3-C3 |  |  |  | ● | ● | ●
P3-C5 | P3-C | Email offer card | Offer in email → one-tap checkout | M | P3-C2,P2-C4 |  |  |  |  | ● | ●
P3-C6 | P3-C | Surface-aware selection | Each surface gets appropriate offer format | M | P3-A4,P3-C1 | [5 empty] | ● | ●
P3-D1 | P3-D | Performance eval job | Underperformer flag on each creative | M | P2-A6,P2-B7 | ● | ●
P3-D2 | P3-D | Creative retirement | Underperformers stop spending | S | P3-D1 |  | ●
P3-D3 | P3-D | Replacement generation | New variants auto-queued | M | P3-D2,P2-B5 |  |  | ● | ●
P3-D4 | P3-D | Creative learning | Generation prompts informed by data | L | P3-D3 |  |  |  | ● | ● | ●
P3-E1 | P3-E | Activity feed | Operators see agents live | L | P3-B5 | ● | ● | ●
P3-E2 | P3-E | Guardrail editor | Non-engineer operators constrain agents | M | P3-A6 |  | ● | ●
P3-E3 | P3-E | Override controls | One-click human override | M | P3-B2 |  |  | ● | ●
P3-E4 | P3-E | Recommendation surface | Human-in-the-loop for high-impact decisions | M | P3-B4 |  |  |  | ● | ●

## Phase 4 — Advanced
Task ID | Track | Task Name | Deliverable | Effort | Depends On | Wk1 | Wk2 | Wk3 | Wk4 | Wk5
P4-A1 | P4-A | LTV prediction model | predictLTV(cohort_features) → {ltv, confidence} | XL | P2-D2,P0-D5 | ● | ● | ● | ●
P4-A2 | P4-A | Financing flow | Approval decision with financing terms | L | P4-A1 |  | ● | ● | ●
P4-A3 | P4-A | Repayment tracking | Revenue attribution and repayment ledger | L | P1-A7,P4-A2 |  |  | ● | ● | ●
P4-A4 | P4-A | Risk controls | Automated risk management | M | P4-A3 |  |  |  | ● | ●
P4-B1 | P4-B | ASO analysis | ASO health score + gap analysis | M | P2-B1 | ● | ●
P4-B2 | P4-B | ASO recommendations | Prioritized ASO action list | M | P4-B1 |  | ● | ●
P4-B3 | P4-B | AI surface discovery | Alert when App surfaced in AI results | M | P0-F3 |  |  | ● | ●
P4-B4 | P4-B | AI surface optimization | App appears in AI surface results | M | P4-B3 |  |  |  | ● | ●
P4-C1 | P4-C | Cohort analysis | Cohort table in analytics DB | L | P2-D2,P0-D4 | ● | ● | ●
P4-C2 | P4-C | LTV projections | Developers see predicted revenue trajectory | L | P4-C1 |  | ● | ● | ●
P4-C3 | P4-C | Payback calculator | Payback period per channel | M | P2-A6,P4-C2 |  |  | ● | ●
P4-C4 | P4-C | Win-back analytics | True incrementality measurement | M | P2-C2,P4-C1 |  |  |  | ● | ●
P4-D1 | P4-D | Churn prediction | predictChurn(user_id) → {probability, top_signals} | XL | P2-D2,P3-A2 | ● | ● | ● | ●
P4-D2 | P4-D | Proactive retention | At-risk users receive targeted action | L | P4-D1,P3-A4 |  | ● | ● | ●
P4-D3 | P4-D | Win-back campaigns | Win-back sequence with incrementally better offers | L | P2-C2,P1-B2 |  |  | ● | ● | ●
P4-D4 | P4-D | Pause subscription | Pause option reduces hard churns | M | P1-A5 |  |  |  | ● | ●

## Staffing
Staffing Allocation by Phase
Role | Phase 0 | Phase 1 | Phase 2 | Phase 3 | Phase 4
Platform / Infra | 3 | 1 | 1 | 1 | 1
Backend Services | 2 | 3 | 3 | 2 | 2
AI / ML | 0 | 0 | 1 | 3 | 2
Frontend / Console | 0 | 2 | 2 | 2 | 1
Mobile SDK | 1 | 2 | 1 | 0 | 0
Compliance | 0 | 1 | 1 | 1 | 0
TOTAL | 6 | 9 | 9 | 9 | 6
Role Responsibilities
Platform / Infra | Cloud, CI/CD, observability, databases, event pipeline, API gateway
Backend Services | MoR layer, offer catalog, web-to-app funnel, lifecycle engine, segment engine, channel integrations
AI / ML | Contextual bandit, training pipelines, LTV prediction, churn prediction, anomaly detection
Frontend / Console | Monetization console, campaign management, creative library, agent console, lifecycle flow builder
Mobile SDK | iOS and Android SDK — identity, events, paywall modules
Compliance | Audit logging, consent propagation, data residency, COPPA, retention policies